## Work Plan
Audit Program and Work Plan
Provider Based Services Audit
Piedmont Healthcare
| How Could Something |  | Examples of Typical Controls |  |  | Est.
Risk | Go Wrong? | Potential Consequence | P = Preventive; D = Detective |  | Audit Steps | Hours | W/P
Conduct necessary planning and background research.
|  |  |  | 1 | Research topic to gain an initial understanding of area/department to be reviewed. | 18
a. Request organization chart for area being reviewed.
b. Examine policies and procedures for area being reviewed.
|  |  |  | 2 | Review prior work conducted for this area.
| Objective - Evaluate regulatory compliance to provider based status for hospital entity. |  |  | 3 | Verify key contacts for the area.
|  |  |  | 4 | Review and revise ICQ as required.
|  |  |  | 5 | Review and revise audit program as required
|  |  |  | 6 | Prepare draft of audit objectives.
| The scope of this audit included: |  |  | 7 | Meet with audit management to discuss project.
| • Review provider-based status for compliance with federal, state and local laws and regulations. • Review provider-based status for compliance with federal, state and local laws and regulations. |  |  | 8 | Alert area of the audit - by phone or email
| • Evaluate controls over hospital facilities doing business off the hospital’s main campus. |  |  | 10 | Contact area and arrange entrance meeting.
|  |  |  | 11 | Send audit announcement letter
|  |  |  | 12 | Conduct entrance meeting to "kick off" project.
|  |  |  | 13 | Finalize audit objectives and scope based on information gathered to date.
I. | Controls are in place to ensure attestations are completed for all off campus provider based locations.
Controls are not in place to ensure attestations are completed for each off campus location. | [5 empty] | 60
A |  |  |  | 1 | Obtain a listing of all locations billing as provider based.
|  |  |  | 2 | Obtain and review a copy of the CMS attestation for each location. Obtain and review the confirmation letter from CMS or the appropriate Government Benefit Administrator (GBA). Resolve any discrepancies.
|  |  |  | 3 | If, location has not completed attestation, obtain data that documents location meets specific provider-based criteria. License The entity operates under the Hospital’s Operating Permit and is approved to operate as such by the Department of Community Health. Clinical Service The clinical services of the entity and the associated Hospital are integrated. Financial Operations The financial operations of the entity and the Hospital are integrated. Public Awareness The entity must is openly held out to the public as a part of the Hospital. Billing • The "PO" modifier is added to every code on the facility bill (UB-04) for services furnished in off-campus provider-based outpatient departments. • Physician services (other than at RHCs) are billed with the correct place-of-service code 19 for off-campus outpatient hospital or 22 for on-campus outpatient hospital. • All Medicare patients are treated, for billing purposes, as hospital outpatients rather than as physician-office patients.
Non-Discrimination Physicians comply with the non-discrimination provisions of 42 USC 489.10 Provider Agreement The entity must comply with the Hospital’s provider agreement. Health and Safety The entity meets all of the health and safety rules applicable to a Medicare participating hospital. EMTALA The entity complies with EMTALA for On-Campus locations treated as a department of the Hospital or Off-Campus locations which are a dedicated emergency department. Resolve any discrepancies.
II. | Policies and procedures are in place regarding provider based status requirements for all hospital entities.
Controls are not in place to ensure all entities are aware of and are following PHC policies and procedures regarding provider based status. |  |  |  |  | Obtain a copy of the policy regarding Provider Based Services and any other entity specific policy referencing guidelines for provider based services. | 40
A |  |  |  | 1 | Review policies and procedures for the minimum topics: • Attestation requirements • Communication channels • Physician billing practices • Approvals • Monitoring
Perform administrative steps to complete the project.
A | Exceptions |  |  | 1 | As issues become apparent, prepare an Exceptions form that documents the issue/root cause/action plan/education/monitoring/accountable leader/implementation date | 8
|  |  |  | 2 | Review all exceptions with audit management and the contact. Obtain audit management's documented approval.
B | Exit Meeting |  |  | 1 | Have an exit meeting with area as may be appropriate. | 2
C | Report Preparation |  |  | 1 | Prepare draft report. | 22
|  |  |  | 2 | Verify the draft report matches key work papers that support issue/root cause/action plan/education/monitoring/accountable leader/implementation date.
|  |  |  | 3 | Have report draft proof read by another auditor.
|  |  |  | 4 | Meet with audit management to get approval of draft report.
|  |  |  | 5 | Send draft report to contact (and others as needed) for responses/ edits etc.
|  |  |  | 6 | Prepare final report.
|  |  |  | 7 | Obtain audit management approval to issue the final report.
[5 empty] | Total Hours | 150